## POCs
Ongoing POCs |  |  |  |  | Team | Lead | Ravish
[6 empty] | Cordinator | Poonam
[6 empty] | Team Members | Adil + Sanjay + Manoj + Viraj
Project/Cust Name
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
1
Project/Cust Name
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark

## Support Automation
Support and Structural Projects |  |  |  |  | Team | Lead | Himanshu/Javed
[6 empty] | Cordinator | Poonam
[6 empty] | Team Members | Adil + Sanjay
Project Name | KBR
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
| P1 | MODULAR SUPPORT 3D CONVERSION (AUTO MTO) | SANJAY J.
| P1 | MODULAR SUPPORT SIDE VIEW ORIENTATION TO BE CORRECTED | ADHIL
| P2 | MODULAR SUPPORT BATCH PRINT TOOL NEEDED

## Thermax P&ID
Thermax P&ID |  |  |  |  | Team | Lead | Abhishek
[6 empty] | Cordinator | Mansi
[6 empty] | Team Members | Manoj , Priyanka, Kiran
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
1 | Medium | General Activities for Report Mngment, support extrct. help, lead generation | Mansi |  | 2026-04-05 |  | To Do
| High | Upgrade Plant 3D Vault API from 2026-2027 | Priyanka | 8 | 2025-04-05 |  | To Do
| High | Application review, tagging philosophy(vault integration) | Abhishek& Kiran, Priyanka | 40 | 2026-05-05 | 2026-08-05 | To Do
| Medium | AI- Plant3D, Vault, AI feature, SDk, R&d | Abhishek& Priyanka | 24 | 2026-11-05

## Thermax ENIMAX
[5 empty] | Team | Lead | Varad
[6 empty] | Co-ordinator | Monika
[6 empty] | Team Members | Vishal + Kiran + Manoj +Viraj
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
| High | Test & close recevied comments on DEV and deploy code on PROD Server | Ankit + Vishal+Adhil +Abhishek |  | 16/03/2026 | 2026-05-05 | In progress
1 | High | Input understanding and mapping with actionable work | Javed + Varad + Vishal | 8 Hrs | 2026-05-05 |  | To Do
2 | High | Start with the planning and actual work based and assigned on Input | Viraj+Vishal+Monika | TBD | 2026-05-05 |  | To Do

## Thermax QA
Thermax P&ID |  |  |  |  | Team | Lead | Varad
[6 empty] | Cordinator | Monika
[6 empty] | Team Members | Ankit
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
1 | Medium | Design Architecture and do Basic Frappe setup for the QC application | Varad+ Sanjana | 8 hrs | 2026-05-05 | 2026-06-05 | To Do

## Samanvay - Engg Memory
Samanvay + Engineering Memory |  |  |  |  | Team | Lead | Abhishek
[6 empty] | Cordinator | Pooja
[6 empty] | Team Members | Ankit + Sanjana
Project Name | Saipem
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
Week 1
Project Name | Luggi
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
1 | High | Naviswork Properties Extraction | Abhishek | 8 hrs | 28-04-26 | 29-04-26 | Done |  | Naviswork API exploration and compilation of properties of all tag id comments
2 | High | Frappe Integration of Naviswork properties against comments | Abhishek | 8 hrs | 30-04-26 | 30-04-26 | Done |  | Master data creation for classification filters
3 | Medium | Auto + Manual comment assignment by their classification criteria | Sanjana | 8 hrs | 30-04-26 | 2026-01-05 | Done |  | Frontend filter Addition
4 | High | Bulk select checkbox bug | Sanjana | 8 hrs | 2026-04-05 | 2026-05-05 | Done
5 | High | Comment Classification API bug | Abhishek | 8 hrs | 2026-05-05 | 2026-05-05 | To Do
Project Name | Thermax
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark
1 | Medium | Design Architecture for AI- Framework | Varad+ Sanjana +Ankit | 4 Hrs(Max) | 2026-05-05 | 2026-06-05 | To Do

## AMC
Loop Drawing Generation | [5 empty] | Team | Lead | Manoj
[7 empty] | Cordinator | Monika
[7 empty] | Team Members | Vishal , Manoj
Project Name
Sr No | Priority | Task Description | Person Responsible | Efforts (Hrs) | Start Date | Target date | Status | Remark